## All Features
Category | Feature | Description | State | Priority | Notes | Owner | Target Date
Auth & Users | User Registration | Sign up with email/password | Production | P0 | Devise-based
Auth & Users | User Login | Email/password authentication | Production | P0 | Working in Phase 1
Auth & Users | User Roles | Admin vs regular user permissions | Production | P0 | Basic role system
Auth & Users | User Profile | View/edit personal information | Production | P1 | Basic profile working
Auth & Users | Password Reset | Email-based password recovery | Test | P1 | Devise provides this
Auth & Users | Multi-factor Auth | 2FA for enhanced security | Idea | P3 | Future consideration
Event Management | Create Event | Admin can create new events | Production | P0 | Working
Event Management | Edit Event | Modify event details | Test | P0 | Needs UAT
Event Management | Delete Event | Remove events | Test | P1 | Needs UAT
Event Management | Event Details | Name, description, date/time | Production | P0 | Complete
Event Management | Event Capacity | Max attendees tracking | Production | P1 | Implemented
Event Management | RSVP Deadline | Cut-off date for responses | Production | P1 | Implemented
Event Management | Event Statistics | Attendee counts, RSVP breakdown | Production | P1 | Admin event show page
Event Management | Event Types | Conference, Convention, Concert, Party | Idea | P2 | Needs design
Event Management | Multi-day Events | Events spanning multiple days | Idea | P2 | Not yet designed
Event Management | Recurring Events | Repeating event templates | Idea | P3 | Future feature
RSVP & Attendance | RSVP Status | Yes/Maybe/No responses | Production | P0 | Fixed in Phase 1
RSVP & Attendance | RSVP Data Model | EventParticipant tracking | Production | P0 | Correct architecture
RSVP & Attendance | RSVP UI | User can change RSVP | Test | P0 | Buttons render, need click test
RSVP & Attendance | View RSVPs | Admin can see all responses | Production | P0 | Working in admin panel
RSVP & Attendance | Quick RSVP (Public) | No-login RSVP via shareable link | Idea | P0 | BLOCKER for Boat Party - needs email workaround
RSVP & Attendance | Waitlist | Queue when event is full | Design | P2 | Needs requirements
RSVP & Attendance | Plus-Ones | Guest attendees | Idea | P2 | Not yet designed
RSVP & Attendance | Check-in | Mark attendees as present | Test | P1 | Feature exists, needs UAT
RSVP & Attendance | QR Code Check-in | Scan to check in | Idea | P2 | Would be valuable
Participant Mgmt | Add Participants | Manually add users to event | Test | P1 | Needs testing
Participant Mgmt | Bulk Invite | Invite multiple users at once | Test | P1 | Exists, needs UAT
Participant Mgmt | Remove Participants | Remove users from event | Test | P2 | Needs testing
Participant Mgmt | Participant List | View all event attendees | Production | P1 | Working
Participant Mgmt | Export CSV | Download participant data | Test | P1 | Feature exists, needs UAT
Participant Mgmt | Import CSV | Bulk import users | Idea | P2 | Not yet implemented
Venue Management | Create Venue | Add venue to system | Production | P1 | Working
Venue Management | Edit Venue | Modify venue details | Test | P1 | Needs UAT
Venue Management | Venue Information | Name, address, capacity | Production | P1 | Basic info working
Venue Management | Multiple Venues | Support many venues | Production | P1 | Architecture supports
Venue Management | Venue Photos | Image uploads for venues | Idea | P3 | Not implemented
Venue Management | Venue Amenities | Track facilities/features | Idea | P3 | Future feature
Communication | Email Notifications | Event updates via email | Dev | P1 | Sidekiq configured, pending test
Communication | RSVP Confirmations | Auto-email on RSVP | Dev | P1 | Mailer exists, needs connection_pool fix
Communication | Bulk Emails | Send to all attendees | Design | P2 | Needs design
Communication | Email Templates | Customizable email layouts | Idea | P2 | Not designed
Communication | SMS Notifications | Text message alerts | Idea | P3 | Future consideration
Communication | In-app Messaging | User-to-user messaging | Idea | P2 | From todo doc
Communication | Social Media Integration | Post to external platforms | Idea | P3 | From todo doc
Admin Features | Admin Dashboard | Overview of all events | Production | P0 | Working with nil checks
Admin Features | Admin Panel | Administrative interface | Production | P0 | Rails Admin or custom
Admin Features | User Management | Admin CRUD for users | Test | P1 | Needs UAT
Admin Features | Event Management | Admin CRUD for events | Production | P0 | Working
Admin Features | Sidekiq Dashboard | Background job monitoring | Production | P1 | Mounted at /admin/sidekiq
Admin Features | Analytics | Event metrics and trends | Idea | P2 | Future feature
Admin Features | Audit Logs | Track admin actions | Idea | P3 | Future feature
Infrastructure | Database (SQLite) | Development database | Production | P0 | Working
Infrastructure | Database (PostgreSQL) | Production database | Design | P0 | Configured but not deployed
Infrastructure | Background Jobs | Sidekiq for async tasks | Test | P1 | Installed, connection_pool issue
Infrastructure | Redis | Cache and job queue | Production | P1 | v7.2.4 installed
Infrastructure | File Uploads | Image/document handling | Idea | P2 | Not implemented
Infrastructure | API | RESTful API endpoints | Idea | P3 | Future feature
Infrastructure | Mobile App | iOS/Android clients | Idea | P3 | Future feature
Infrastructure | Deployment Pipeline | CI/CD automation | Idea | P2 | Not set up
Contact Enhancement | Multiple Emails | Primary, secondary emails per user | Idea | P2 | Phase 2 - entity enhancement
Contact Enhancement | Multiple Phone Numbers | Mobile, home, office numbers | Idea | P2 | Enhanced contact info
Contact Enhancement | Multiple Addresses | Home, work, mailing addresses | Idea | P2 | For physical invites
Contact Enhancement | Social Media Links | Facebook, LinkedIn, Twitter profiles | Idea | P2 | Professional networking
Contact Enhancement | Vendor Profiles | Business information for vendors | Idea | P2 | Vendor management
Contact Enhancement | Venue Profiles | Enhanced venue data | Idea | P2 | Better venue tracking
Resource Matching | User Profiles Enhanced | Skills, interests, resources | Idea | P2 | Pin for later discussion
Resource Matching | Resource Tags | Categorization system | Idea | P2 | Replacement for old tags
Resource Matching | AI-driven Matching | Smart recommendations | Idea | P3 | Interesting concept
Resource Matching | Rideshare Matching | Connect attendees for travel | Idea | P3 | Specific use case
Resource Matching | Interest Groups | Pokemon example, etc. | Idea | P3 | Community building
Event Types | Conference Type | Booths, speakers, sessions | Idea | P2 | Specialized features
Event Types | Convention Type | Vendor halls, panels | Idea | P2 | Your sweet spot
Event Types | Concert Type | Ticketing, seating | Idea | P3 | Different model
Event Types | Party Type | Casual gatherings | Idea | P3 | Simpler features
Event Types | Booth Management | Vendor booth assignments | Idea | P2 | Convention-specific
Event Types | Speaker Management | Track speakers/panels | Idea | P2 | Conference-specific
Event Types | Session Scheduling | Conference sessions | Idea | P2 | Complex feature
Messaging (Advanced) | Protected User Messaging | In-app communication with privacy | Idea | P2 | Privacy considerations
Messaging (Advanced) | Vendor Broadcasts | Vendors message attendees | Idea | P2 | Marketing capability
Messaging (Advanced) | Event Announcements | Official event messages | Idea | P2 | Communication tool
Messaging (Advanced) | Message Permissions | Who can message whom | Idea | P2 | Privacy/safety
Marketplace | Vendor Marketplace | In/out of event sales | Idea | P3 | Revenue opportunity
Marketplace | Cryptocurrency Support | Payment innovation | Idea | P3 | Needs definition
Marketplace | POS Integration | Point of sale systems | Idea | P3 | Long-term integration
Marketplace | Payment Processing | Stripe/PayPal | Idea | P2 | For paid events
Marketplace | Ticketing | Paid ticket sales | Idea | P2 | Revenue feature
Marketplace | Subscription Model | Recurring revenue | Idea | P3 | Business model
Testing & Quality | Unit Tests | Model/controller tests | Design | P1 | Minimal coverage
Testing & Quality | Integration Tests | End-to-end testing | Idea | P1 | Not implemented
Testing & Quality | Performance Tests | Load/stress testing with FactoryBot | Idea | P2 | Need setup
Testing & Quality | Security Audit | Vulnerability assessment | Idea | P2 | Pre-production
Testing & Quality | Accessibility | WCAG compliance | Idea | P3 | Future consideration

## By Priority
Category | Feature | Description | State | Priority | Notes | Owner | Target Date
Infrastructure | Database (PostgreSQL) | Production database | Design | P0 | Configured but not deployed
RSVP & Attendance | Quick RSVP (Public) | No-login RSVP via shareable link | Idea | P0 | BLOCKER for Boat Party - needs email workaround
Auth & Users | User Registration | Sign up with email/password | Production | P0 | Devise-based
Auth & Users | User Login | Email/password authentication | Production | P0 | Working in Phase 1
Auth & Users | User Roles | Admin vs regular user permissions | Production | P0 | Basic role system
Event Management | Create Event | Admin can create new events | Production | P0 | Working
Event Management | Event Details | Name, description, date/time | Production | P0 | Complete
RSVP & Attendance | RSVP Status | Yes/Maybe/No responses | Production | P0 | Fixed in Phase 1
RSVP & Attendance | RSVP Data Model | EventParticipant tracking | Production | P0 | Correct architecture
RSVP & Attendance | View RSVPs | Admin can see all responses | Production | P0 | Working in admin panel
Admin Features | Admin Dashboard | Overview of all events | Production | P0 | Working with nil checks
Admin Features | Admin Panel | Administrative interface | Production | P0 | Rails Admin or custom
Admin Features | Event Management | Admin CRUD for events | Production | P0 | Working
Infrastructure | Database (SQLite) | Development database | Production | P0 | Working
Event Management | Edit Event | Modify event details | Test | P0 | Needs UAT
RSVP & Attendance | RSVP UI | User can change RSVP | Test | P0 | Buttons render, need click test
Testing & Quality | Unit Tests | Model/controller tests | Design | P1 | Minimal coverage
Communication | Email Notifications | Event updates via email | Dev | P1 | Sidekiq configured, pending test
Communication | RSVP Confirmations | Auto-email on RSVP | Dev | P1 | Mailer exists, needs connection_pool fix
Testing & Quality | Integration Tests | End-to-end testing | Idea | P1 | Not implemented
Auth & Users | User Profile | View/edit personal information | Production | P1 | Basic profile working
Event Management | Event Capacity | Max attendees tracking | Production | P1 | Implemented
Event Management | RSVP Deadline | Cut-off date for responses | Production | P1 | Implemented
Event Management | Event Statistics | Attendee counts, RSVP breakdown | Production | P1 | Admin event show page
Participant Mgmt | Participant List | View all event attendees | Production | P1 | Working
Venue Management | Create Venue | Add venue to system | Production | P1 | Working
Venue Management | Venue Information | Name, address, capacity | Production | P1 | Basic info working
Venue Management | Multiple Venues | Support many venues | Production | P1 | Architecture supports
Admin Features | Sidekiq Dashboard | Background job monitoring | Production | P1 | Mounted at /admin/sidekiq
Infrastructure | Redis | Cache and job queue | Production | P1 | v7.2.4 installed
Auth & Users | Password Reset | Email-based password recovery | Test | P1 | Devise provides this
Event Management | Delete Event | Remove events | Test | P1 | Needs UAT
RSVP & Attendance | Check-in | Mark attendees as present | Test | P1 | Feature exists, needs UAT
Participant Mgmt | Add Participants | Manually add users to event | Test | P1 | Needs testing
Participant Mgmt | Bulk Invite | Invite multiple users at once | Test | P1 | Exists, needs UAT
Participant Mgmt | Export CSV | Download participant data | Test | P1 | Feature exists, needs UAT
Venue Management | Edit Venue | Modify venue details | Test | P1 | Needs UAT
Admin Features | User Management | Admin CRUD for users | Test | P1 | Needs UAT
Infrastructure | Background Jobs | Sidekiq for async tasks | Test | P1 | Installed, connection_pool issue
RSVP & Attendance | Waitlist | Queue when event is full | Design | P2 | Needs requirements
Communication | Bulk Emails | Send to all attendees | Design | P2 | Needs design
Event Management | Event Types | Conference, Convention, Concert, Party | Idea | P2 | Needs design
Event Management | Multi-day Events | Events spanning multiple days | Idea | P2 | Not yet designed
RSVP & Attendance | Plus-Ones | Guest attendees | Idea | P2 | Not yet designed
RSVP & Attendance | QR Code Check-in | Scan to check in | Idea | P2 | Would be valuable
Participant Mgmt | Import CSV | Bulk import users | Idea | P2 | Not yet implemented
Communication | Email Templates | Customizable email layouts | Idea | P2 | Not designed
Communication | In-app Messaging | User-to-user messaging | Idea | P2 | From todo doc
Admin Features | Analytics | Event metrics and trends | Idea | P2 | Future feature
Infrastructure | File Uploads | Image/document handling | Idea | P2 | Not implemented
Infrastructure | Deployment Pipeline | CI/CD automation | Idea | P2 | Not set up
Contact Enhancement | Multiple Emails | Primary, secondary emails per user | Idea | P2 | Phase 2 - entity enhancement
Contact Enhancement | Multiple Phone Numbers | Mobile, home, office numbers | Idea | P2 | Enhanced contact info
Contact Enhancement | Multiple Addresses | Home, work, mailing addresses | Idea | P2 | For physical invites
Contact Enhancement | Social Media Links | Facebook, LinkedIn, Twitter profiles | Idea | P2 | Professional networking
Contact Enhancement | Vendor Profiles | Business information for vendors | Idea | P2 | Vendor management
Contact Enhancement | Venue Profiles | Enhanced venue data | Idea | P2 | Better venue tracking
Resource Matching | User Profiles Enhanced | Skills, interests, resources | Idea | P2 | Pin for later discussion
Resource Matching | Resource Tags | Categorization system | Idea | P2 | Replacement for old tags
Event Types | Conference Type | Booths, speakers, sessions | Idea | P2 | Specialized features
Event Types | Convention Type | Vendor halls, panels | Idea | P2 | Your sweet spot
Event Types | Booth Management | Vendor booth assignments | Idea | P2 | Convention-specific
Event Types | Speaker Management | Track speakers/panels | Idea | P2 | Conference-specific
Event Types | Session Scheduling | Conference sessions | Idea | P2 | Complex feature
Messaging (Advanced) | Protected User Messaging | In-app communication with privacy | Idea | P2 | Privacy considerations
Messaging (Advanced) | Vendor Broadcasts | Vendors message attendees | Idea | P2 | Marketing capability
Messaging (Advanced) | Event Announcements | Official event messages | Idea | P2 | Communication tool
Messaging (Advanced) | Message Permissions | Who can message whom | Idea | P2 | Privacy/safety
Marketplace | Payment Processing | Stripe/PayPal | Idea | P2 | For paid events
Marketplace | Ticketing | Paid ticket sales | Idea | P2 | Revenue feature
Testing & Quality | Performance Tests | Load/stress testing with FactoryBot | Idea | P2 | Need setup
Testing & Quality | Security Audit | Vulnerability assessment | Idea | P2 | Pre-production
Participant Mgmt | Remove Participants | Remove users from event | Test | P2 | Needs testing
Auth & Users | Multi-factor Auth | 2FA for enhanced security | Idea | P3 | Future consideration
Event Management | Recurring Events | Repeating event templates | Idea | P3 | Future feature
Venue Management | Venue Photos | Image uploads for venues | Idea | P3 | Not implemented
Venue Management | Venue Amenities | Track facilities/features | Idea | P3 | Future feature
Communication | SMS Notifications | Text message alerts | Idea | P3 | Future consideration
Communication | Social Media Integration | Post to external platforms | Idea | P3 | From todo doc
Admin Features | Audit Logs | Track admin actions | Idea | P3 | Future feature
Infrastructure | API | RESTful API endpoints | Idea | P3 | Future feature
Infrastructure | Mobile App | iOS/Android clients | Idea | P3 | Future feature
Resource Matching | AI-driven Matching | Smart recommendations | Idea | P3 | Interesting concept
Resource Matching | Rideshare Matching | Connect attendees for travel | Idea | P3 | Specific use case
Resource Matching | Interest Groups | Pokemon example, etc. | Idea | P3 | Community building
Event Types | Concert Type | Ticketing, seating | Idea | P3 | Different model
Event Types | Party Type | Casual gatherings | Idea | P3 | Simpler features
Marketplace | Vendor Marketplace | In/out of event sales | Idea | P3 | Revenue opportunity
Marketplace | Cryptocurrency Support | Payment innovation | Idea | P3 | Needs definition
Marketplace | POS Integration | Point of sale systems | Idea | P3 | Long-term integration
Marketplace | Subscription Model | Recurring revenue | Idea | P3 | Business model
Testing & Quality | Accessibility | WCAG compliance | Idea | P3 | Future consideration

## By State
Category | Feature | Description | State | Priority | Notes | Owner | Target Date
Auth & Users | User Registration | Sign up with email/password | Production | P0 | Devise-based
Auth & Users | User Login | Email/password authentication | Production | P0 | Working in Phase 1
Auth & Users | User Roles | Admin vs regular user permissions | Production | P0 | Basic role system
Event Management | Create Event | Admin can create new events | Production | P0 | Working
Event Management | Event Details | Name, description, date/time | Production | P0 | Complete
RSVP & Attendance | RSVP Status | Yes/Maybe/No responses | Production | P0 | Fixed in Phase 1
RSVP & Attendance | RSVP Data Model | EventParticipant tracking | Production | P0 | Correct architecture
RSVP & Attendance | View RSVPs | Admin can see all responses | Production | P0 | Working in admin panel
Admin Features | Admin Dashboard | Overview of all events | Production | P0 | Working with nil checks
Admin Features | Admin Panel | Administrative interface | Production | P0 | Rails Admin or custom
Admin Features | Event Management | Admin CRUD for events | Production | P0 | Working
Infrastructure | Database (SQLite) | Development database | Production | P0 | Working
Auth & Users | User Profile | View/edit personal information | Production | P1 | Basic profile working
Event Management | Event Capacity | Max attendees tracking | Production | P1 | Implemented
Event Management | RSVP Deadline | Cut-off date for responses | Production | P1 | Implemented
Event Management | Event Statistics | Attendee counts, RSVP breakdown | Production | P1 | Admin event show page
Participant Mgmt | Participant List | View all event attendees | Production | P1 | Working
Venue Management | Create Venue | Add venue to system | Production | P1 | Working
Venue Management | Venue Information | Name, address, capacity | Production | P1 | Basic info working
Venue Management | Multiple Venues | Support many venues | Production | P1 | Architecture supports
Admin Features | Sidekiq Dashboard | Background job monitoring | Production | P1 | Mounted at /admin/sidekiq
Infrastructure | Redis | Cache and job queue | Production | P1 | v7.2.4 installed
Event Management | Edit Event | Modify event details | Test | P0 | Needs UAT
RSVP & Attendance | RSVP UI | User can change RSVP | Test | P0 | Buttons render, need click test
Auth & Users | Password Reset | Email-based password recovery | Test | P1 | Devise provides this
Event Management | Delete Event | Remove events | Test | P1 | Needs UAT
RSVP & Attendance | Check-in | Mark attendees as present | Test | P1 | Feature exists, needs UAT
Participant Mgmt | Add Participants | Manually add users to event | Test | P1 | Needs testing
Participant Mgmt | Bulk Invite | Invite multiple users at once | Test | P1 | Exists, needs UAT
Participant Mgmt | Export CSV | Download participant data | Test | P1 | Feature exists, needs UAT
Venue Management | Edit Venue | Modify venue details | Test | P1 | Needs UAT
Admin Features | User Management | Admin CRUD for users | Test | P1 | Needs UAT
Infrastructure | Background Jobs | Sidekiq for async tasks | Test | P1 | Installed, connection_pool issue
Participant Mgmt | Remove Participants | Remove users from event | Test | P2 | Needs testing
Communication | Email Notifications | Event updates via email | Dev | P1 | Sidekiq configured, pending test
Communication | RSVP Confirmations | Auto-email on RSVP | Dev | P1 | Mailer exists, needs connection_pool fix
Infrastructure | Database (PostgreSQL) | Production database | Design | P0 | Configured but not deployed
Testing & Quality | Unit Tests | Model/controller tests | Design | P1 | Minimal coverage
RSVP & Attendance | Waitlist | Queue when event is full | Design | P2 | Needs requirements
Communication | Bulk Emails | Send to all attendees | Design | P2 | Needs design
RSVP & Attendance | Quick RSVP (Public) | No-login RSVP via shareable link | Idea | P0 | BLOCKER for Boat Party - needs email workaround
Testing & Quality | Integration Tests | End-to-end testing | Idea | P1 | Not implemented
Event Management | Event Types | Conference, Convention, Concert, Party | Idea | P2 | Needs design
Event Management | Multi-day Events | Events spanning multiple days | Idea | P2 | Not yet designed
RSVP & Attendance | Plus-Ones | Guest attendees | Idea | P2 | Not yet designed
RSVP & Attendance | QR Code Check-in | Scan to check in | Idea | P2 | Would be valuable
Participant Mgmt | Import CSV | Bulk import users | Idea | P2 | Not yet implemented
Communication | Email Templates | Customizable email layouts | Idea | P2 | Not designed
Communication | In-app Messaging | User-to-user messaging | Idea | P2 | From todo doc
Admin Features | Analytics | Event metrics and trends | Idea | P2 | Future feature
Infrastructure | File Uploads | Image/document handling | Idea | P2 | Not implemented
Infrastructure | Deployment Pipeline | CI/CD automation | Idea | P2 | Not set up
Contact Enhancement | Multiple Emails | Primary, secondary emails per user | Idea | P2 | Phase 2 - entity enhancement
Contact Enhancement | Multiple Phone Numbers | Mobile, home, office numbers | Idea | P2 | Enhanced contact info
Contact Enhancement | Multiple Addresses | Home, work, mailing addresses | Idea | P2 | For physical invites
Contact Enhancement | Social Media Links | Facebook, LinkedIn, Twitter profiles | Idea | P2 | Professional networking
Contact Enhancement | Vendor Profiles | Business information for vendors | Idea | P2 | Vendor management
Contact Enhancement | Venue Profiles | Enhanced venue data | Idea | P2 | Better venue tracking
Resource Matching | User Profiles Enhanced | Skills, interests, resources | Idea | P2 | Pin for later discussion
Resource Matching | Resource Tags | Categorization system | Idea | P2 | Replacement for old tags
Event Types | Conference Type | Booths, speakers, sessions | Idea | P2 | Specialized features
Event Types | Convention Type | Vendor halls, panels | Idea | P2 | Your sweet spot
Event Types | Booth Management | Vendor booth assignments | Idea | P2 | Convention-specific
Event Types | Speaker Management | Track speakers/panels | Idea | P2 | Conference-specific
Event Types | Session Scheduling | Conference sessions | Idea | P2 | Complex feature
Messaging (Advanced) | Protected User Messaging | In-app communication with privacy | Idea | P2 | Privacy considerations
Messaging (Advanced) | Vendor Broadcasts | Vendors message attendees | Idea | P2 | Marketing capability
Messaging (Advanced) | Event Announcements | Official event messages | Idea | P2 | Communication tool
Messaging (Advanced) | Message Permissions | Who can message whom | Idea | P2 | Privacy/safety
Marketplace | Payment Processing | Stripe/PayPal | Idea | P2 | For paid events
Marketplace | Ticketing | Paid ticket sales | Idea | P2 | Revenue feature
Testing & Quality | Performance Tests | Load/stress testing with FactoryBot | Idea | P2 | Need setup
Testing & Quality | Security Audit | Vulnerability assessment | Idea | P2 | Pre-production
Auth & Users | Multi-factor Auth | 2FA for enhanced security | Idea | P3 | Future consideration
Event Management | Recurring Events | Repeating event templates | Idea | P3 | Future feature
Venue Management | Venue Photos | Image uploads for venues | Idea | P3 | Not implemented
Venue Management | Venue Amenities | Track facilities/features | Idea | P3 | Future feature
Communication | SMS Notifications | Text message alerts | Idea | P3 | Future consideration
Communication | Social Media Integration | Post to external platforms | Idea | P3 | From todo doc
Admin Features | Audit Logs | Track admin actions | Idea | P3 | Future feature
Infrastructure | API | RESTful API endpoints | Idea | P3 | Future feature
Infrastructure | Mobile App | iOS/Android clients | Idea | P3 | Future feature
Resource Matching | AI-driven Matching | Smart recommendations | Idea | P3 | Interesting concept
Resource Matching | Rideshare Matching | Connect attendees for travel | Idea | P3 | Specific use case
Resource Matching | Interest Groups | Pokemon example, etc. | Idea | P3 | Community building
Event Types | Concert Type | Ticketing, seating | Idea | P3 | Different model
Event Types | Party Type | Casual gatherings | Idea | P3 | Simpler features
Marketplace | Vendor Marketplace | In/out of event sales | Idea | P3 | Revenue opportunity
Marketplace | Cryptocurrency Support | Payment innovation | Idea | P3 | Needs definition
Marketplace | POS Integration | Point of sale systems | Idea | P3 | Long-term integration
Marketplace | Subscription Model | Recurring revenue | Idea | P3 | Business model
Testing & Quality | Accessibility | WCAG compliance | Idea | P3 | Future consideration

## Summary Dashboard
CONFAB/EVM1 FEATURE INVENTORY SUMMARY
Generated: | February 14, 2026
Total Features: | 92
FEATURES BY STATE
State | Count | Percentage
Production | 22 | 23.91%
Test | 12 | 13.04%
Dev | 2 | 2.174%
Design | 4 | 4.348%
UAT | 0 | 0%
Idea | 52 | 56.52%
FEATURES BY PRIORITY
Priority | Count | Percentage
P0 | 16 | 17.39%
P1 | 23 | 25%
P2 | 34 | 36.96%
P3 | 19 | 20.65%
TOP CATEGORIES
Category | Count
Event Management | 10
RSVP & Attendance | 9
Communication | 7
Admin Features | 7
Infrastructure | 8
Contact Enhancement | 6
Resource Matching | 5

## Next Actions
IMMEDIATE NEXT ACTIONS
Priority | Action Item | Category
P0 | Design & implement Quick RSVP (public RSVP link, no email required) | RSVP & Attendance
P0 | Test RSVP UI - verify buttons actually change status | RSVP & Attendance
P0 | Fix Sidekiq connection_pool issue | Infrastructure
P0 | Rename project ev1 → evm1 and move to C:\evm1 | Infrastructure
P1 | Test bulk invite functionality | Participant Mgmt
P1 | Test check-in system | RSVP & Attendance
P1 | Verify email notifications work after Sidekiq fix | Communication
P1 | Complete UAT on all "Test" state features | Testing & Quality
P1 | Set up FactoryBot for volume testing | Testing & Quality
P2 | Design contact/identity enhancement (multiple emails, phones) | Contact Enhancement
P2 | Decide on event type specialization (Conference vs Convention) | Event Types
P2 | Explore rebranding options (Confab vs other names) | Admin Features
P2 | Create training materials for 3-10 helpers | Admin Features
P3 | Document resource matching concept for future discussion | Resource Matching
KEY BLOCKERS FOR BOAT ANNIVERSARY PARTY
1. Quick RSVP feature (no email required) - people are on Facebook, not in email list
2. Email notification working (fix Sidekiq connection_pool)
3. Testing RSVP button functionality